ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	3

2.	OBJECTIVES & EXPECTED OUTPUTS	3

2.1.	Overall objective	3

2.2.	Specific objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	4

3.	ASSUMPTIONS & RISKS	6

3.1.	Assumptions underlying the project	6

3.2.	Risks	6

4.	SCOPE OF THE WORK	7

4.1.	General	9

4.2.	Specific work	11

4.3.	Project management	18

5.	LOGISTICS AND TIMING	19

5.1.	Location	19

5.2.	Start date & period of implementation of tasks	21

6.	REQUIREMENTS	21

6.1.	Personnel	21

6.2.	Office accommodation	23

6.3.	Facilities to be provided by the contractor	23

6.4.	Equipment	23

7.	REPORTS	23

7.1.	Reporting requirements	23

7.2.	Submission and approval of reports	23

8.	MONITORING AND EVALUATION	25

8.1.	Definition of indicators	25

8.2.	Special requirements	26

# BACKGROUND INFORMATION

## Partner country

Bulgaria - Türkiye

## Contracting authority

Trakya Development Agency

## Country background

Türkiye is a country with a strategic geographic location and a diversified tourism sector that makes a significant contribution to economic development and employment. Tourism policies at national and regional levels increasingly focus on the diversification of tourism products beyond mass tourism, with particular emphasis on cultural heritage, gastronomy, eco-tourism, rural tourism and sustainable destination development. These priorities are supported by investments in heritage conservation, destination branding and digital tourism solutions.

Despite recent global economic challenges and the impacts of the COVID-19 pandemic, Türkiye’s tourism sector has demonstrated a high level of resilience and recovery, especially in regional and cross-border tourism flows. From a social perspective, strong traditions of hospitality, an active local stakeholder base and high cross-border mobility in the Trakya region support the implementation of cooperative tourism initiatives.

## Current situation in the sector

- The Trakya Region, located in north-western Türkiye and bordering Bulgaria, has strong potential for cross-border tourism development due to its shared cultural heritage, historical ties, natural assets and terroir-based traditions. Kırklareli Province, in particular, offers a combination of vineyards, protected natural areas, local gastronomy and cultural sites, which are well aligned with emerging demand for experience-based and sustainable tourism. The region maintains close social, cultural and economic linkages with Pomorie (Bulgaria), creating favourable conditions for the development of joint tourism routes and cross-border tourism products.

- A key challenge in the region remains the predominance of short-term and day-trip visits, which limits local economic impact and the depth of visitor engagement. Addressing this challenge requires the development of integrated tourism routes, diversified tourism experiences and improved digital visibility. In this context, the Pomorie–Kırklareli Terroir & Traditions Tourism Route aims to transform short visits into longer, value-added stays by promoting cultural, gastronomic and eco-tourism experiences, in line with sustainable tourism and green transition objectives.

- In this context, the Trakya Development Agency plays a key role in supporting sustainable and diversified tourism development in the region. The Agency has been actively involved in strengthening regional tourism infrastructure, promoting local products and terroir-based values, and supporting destination branding and cross-border cooperation initiatives.

- Within the framework of the INTERREG VI-A IPA Bulgaria–Turkey Programme, the Trakya Development Agency contributes to result-oriented cross-border cooperation by supporting joint tourism products, coordinated destination promotion and sustainable tourism models. The Agency focuses on delivering tangible outputs such as integrated tourism routes, shared branding tools and digital solutions that enhance visitor experience and extend length of stay. These interventions directly support programme results related to increased cross-border attractiveness, improved territorial integration and strengthened institutional cooperation between Kırklareli and Pomorie.

## Related programmes and other donor activities

N/A

# OBJECTIVES & EXPECTED OUTPUTS

## Overall objective

The overall objective (Impact) to which this action contributes is the enhancement of sustainable cross-border tourism cooperation between Bulgaria and Türkiye, contributing to the long-term economic development and territorial cohesion of the Kırklareli–Pomorie border area through diversified, experience-based and environmentally responsible tourism. This action supports the expected results of the INTERREG VI-A IPA Bulgaria–Turkey Programme by increasing the cross-border attractiveness of the joint destination, strengthening institutional cooperation, and improving territorial integration through shared tourism products, common branding and digital solutions that extend the length of visitor stays and raise the value-added impact of tourism in both regions.

## Specific objective(s)

The specific objectives of this contract are as follows:

- The Pomorie–Kırklareli Terroir & Traditions Tourism Route is strategically planned, branded and operationally ready, with a coherent identity, evidence-based strategic framework and practical sustainability guidance available to partners and stakeholders.

- The visibility and attractiveness of the Pomorie–Kırklareli cross-border tourist area is enhanced through professional visual content, promotional materials and active media/digital outreach, resulting in increased awareness among target visitor segments.

- Cross-border cooperation and joint destination management between Pomorie and Kırklareli is strengthened through coordinated event delivery, stakeholder engagement, partner meetings and shared digital tools.

## Expected outputs to be achieved by the contractor

The service will be paid on the basis of the delivery of the specified output(s). Payments might be totally or partially withheld if the contractual result(s) have not been reached in conformity with the detailed terms of reference. Payment(s) is/are based on the approval of this/these deliverable(s). Partial payment has to be determined according to the partial implementation of the output(s).

The expected outputs of this contract are as follows:

Outcome 1 (O1) – Lot 1: Strategy Development (BC 4.2)

To establish a coherent, evidence-based and participatory strategic framework for the sustainable development and long-term management of the Pomorie–Kırklareli Terroir & Traditions Tourism Route, enabling partners and local stakeholders to coordinate and implement route development in a structured manner.

Outcome 2 (O2) – Lot 2: Creative Design and Visual Production (BC 4.4–BC 4.5)

To develop and deliver a unified brand identity and high-quality creative/visual assets that strengthen the route’s image and visibility, ensuring consistent communication and attractive promotional content across channels.

Outcome 3 (O3) – Lot 3: Printing Services (BC 4.6)

To ensure the timely printing and delivery of high-quality promotional materials supporting effective dissemination and visibility of the tourism route in cross-border region of Bulgaria - Türkiye.

Outcome 4 (O4) – Lot 4: PR, Events & Travel Services (BC 4.1 / BC 4.3 / BC 4.7 / BC 4.8)

To increase the route’s outreach, attractiveness and stakeholder engagement through coordinated PR and multichannel promotion, meetings/events (festivals) and cross-border travel support for events, contributing to enhanced cross-border tourism cooperation and visitor interest.

Outcome 5 (O5) – Lot 5: Digital & Green Transformation Activities (BC 4.9)

To enhance the route’s accessibility and sustainable tourism offer through the design and development of a smart mobile application and website, including offline access to key information and an integrated sustainability tracking and reporting feature for businesses and visitors.

- Outputs to Outcome 1 (O1) – Lot 1 (BC 4.2)

- Output 1.1 (Lot 1 / BC 4.2 → O1): Integrated Strategic Framework (final, approved).

- Output 1.2 (Lot 1 / BC 4.2 → O1): SWOT Analysis (final, approved).

- Output 1.3 (Lot 1 / BC 4.2 → O1): Stakeholder Mapping & Engagement Output (final, approved).

- Output 1.4 (Lot 1 / BC 4.2 → O1): Market Research Report / Summary (final, approved).

- Output 1.5 (Lot 1 / BC 4.2 → O1): Sustainable Tourism Practices Guide (final, approved).

- Outputs to Outcome 2 (O2) – Lot 2 (BC 4.4–BC 4.5)

- Output 2.1 (Lot 2 / BC 4.4 → O2): Common Brand Story & Visual Identity Package (incl. brand guidelines and editable templates) (final, approved).

- Output 2.2 (Lot 2 / BC 4.5 → O2): Route mapping and promotional design assets (print-ready + digital formats) (final, approved).

- Output 2.3 (Lot 2 / BC 4.5 → O2): Photography package delivered (as per ToR requirements) (final, approved).

- Output 2.4 (Lot 2 / BC 4.5 → O2): Video/film outputs delivered (as per ToR requirements) (final, approved).

- Outputs to Outcome 3 (O3) – Lot 3 (BC 4.6)

- Output 3.1 (Lot 3 / BC 4.6 → O3): Printing and delivery of 1,000 maps (delivered and accepted).

- Output 3.2 (Lot 3 / BC 4.6 → O3): Printing and delivery of 1,000 brochures (delivered and accepted).

- Output 3.3 (Lot 3 / BC 4.6 → O3): Printing and delivery of 1,000 visitor guides (delivered and accepted).

- Output 3.4 (Lot 3 / BC 4.6 → O3): Printing and delivery of 1,000 postcards (delivered and accepted).

- Outputs to Outcome 4 (O4) – Lot 4 (BC 4.1 / BC 4.3 / BC 4.7 / BC 4.8)

- Output 4.1 (Lot 4 / BC 4.1 → O4): Partners’ Meeting in Kırklareli delivered (materials + translation + coffee break + coordination).

- Output 4.2 (Lot 4 / BC 4.3 → O4): Travel/transport and vehicle allocation service delivered (as specified).

- Output 4.3 (Lot 4 / BC 4.7 → O4): PR & Multichannel Promotion Plan delivered (final, approved).

- Output 4.4 (Lot 4 / BC 4.7 → O4): Press releases prepared and disseminated (as per agreed plan).

- Output 4.5 (Lot 4 / BC 4.7 → O4): Editorial content delivered (as per agreed plan).

- Output 4.6 (Lot 4 / BC 4.7 → O4): Media familiarisation trip(s) delivered (as per agreed plan).

- Output 4.7 (Lot 4 / BC 4.7 → O4): Social media management/content delivery and basic performance reporting (as per agreed plan).

- Output 4.8 (Lot 4 / BC 4.7 → O4): Influencer/expert collaborations delivered (as per agreed plan).

- Output 4.9 (Lot 4 / BC 4.8 → O4): Two-day Terroir & Traditions Festival in Türkiye delivered (full organisation + logistics + technical set-up + accommodation/meals + on-site management).

- Outputs to Outcome 5 (O5) – Lot 5 (BC 4.9)

- Output 5.1 (Lot 5 / BC 4.9 → O5): Mobile Application Design & Web Site Development (final build delivered, ready for deployment).

- Output 5.2 (Lot 5 / BC 4.9 → O5): Sustainability Tracking & Reporting System implemented (monitoring/reporting + insights).

- Output 5.3 (Lot 5 / BC 4.9 → O5): Content Management & User Information structured and presented in a user-friendly format.

- Output 5.4 (Lot 5 / BC 4.9 → O5): Final Delivery & Documentation (user guidance + admin/content update guidance + handover notes).

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

The successful implementation of the assignment is based on the following assumptions:

- Stakeholder cooperation and access: Project partners, local authorities and relevant tourism stakeholders in both countries will cooperate in a timely manner, provide access to necessary information and participate in consultations/meetings as required.

- Timely approvals and feedback: The Contracting Authority and project partners will provide consolidated comments and approvals on draft deliverables within agreed timeframes to avoid delays in production, publication or event delivery.

- Availability of data and content inputs: Required background materials (existing studies, route-related information, points of interest, maps, logos/visibility templates, contact lists, etc.) will be made available to the Contractor in due time and in usable formats.

- Rights and permissions: All necessary permissions for the use of third-party content (photos, music, footage, editorial materials), as well as filming/photography permissions at relevant sites, can be obtained in a timely manner. Where required, partners will facilitate access and permissions.

- Cross-border mobility and logistics: Cross-border travel and logistics (participant travel, transport routes, deliveries to Pomorie/Kırklareli, accommodation arrangements) will be feasible during implementation, without extraordinary restrictions that would prevent planned activities.

- Venue and supplier availability: Venues, accommodation facilities, catering providers and technical suppliers required for meetings/festivals and related logistics will be available at market conditions and within the planned schedule.

- Technical feasibility and access: For the digital components (website/mobile application), adequate access to hosting/domain resources (if applicable), relevant accounts, and required technical inputs will be provided or facilitated by the Contracting Authority; and the necessary technical conditions (connectivity for testing, device access for QA) will be available.

- Budget and unit price assumptions: The estimated budgets and market conditions remain broadly stable during the implementation period (e.g., printing, transport, accommodation, technical rental), and any significant changes will be addressed through agreed contract mechanisms.

- Visibility requirements clarity: Project communication and visibility requirements (logos, disclaimers, branding rules) will be clearly communicated and applied consistently across all lots and deliverables.

## Risks

The main risks that may affect implementation of the assignment are the following:

- Delays in approvals and consolidated feedback: Late or fragmented comments/approvals from the Contracting Authority and/or partners may delay production cycles (design, printing, publications) and the delivery of events and digital outputs.

- Stakeholder availability and engagement risks: Key stakeholders (local authorities, tourism actors, media/influencers) may have limited availability or reduced willingness to participate, affecting consultations, stakeholder mapping, fam trips and outreach activities.

- Cross-border travel and logistics disruptions: Changes in travel conditions, border procedures, transport disruptions, or unforeseen restrictions may affect participant mobility, transport services (Kırklareli–Pomorie), and the organisation of cross-border activities.

- Procurement and supplier availability risks: Limited availability of suitable venues, accommodation capacity, catering providers or technical equipment suppliers (stage/sound/lighting) during peak periods may impact event scheduling, service quality and costs.

- Cost volatility: Inflation or market price fluctuations (printing, fuel/transport, accommodation, equipment rental) may create budget pressure and require early planning and efficient scheduling to remain within contractual ceilings.

- Quality risks for printed materials: Production errors (colour inconsistencies, trimming defects, packaging damage) or delivery damage may lead to reprints and schedule impacts if quality control and acceptance procedures are not applied.

- Media/influencer performance uncertainty: PR outputs may not translate into expected coverage due to editorial decisions, algorithm changes on social media platforms, seasonal news cycles, or influencer performance variability.

- Content rights and permissions risks: Delays or failure to secure permissions for photography/filming, locations, third-party visuals, music or editorial re-use may restrict content production and publication, or lead to compliance issues.

- Digital development risks (app/website): Technical complexity (offline maps, sustainability tracking), device/platform compatibility issues, integration constraints and late content inputs may cause delays, defects or reduced functionality if not managed through phased testing and clear acceptance criteria.

- Data accuracy and sustainability-method risks: Sustainability tracking/reporting features may be challenged by unclear definitions, inconsistent data entry by users/businesses or insufficient methodological guidance, reducing usability and credibility.

- Security and privacy risks for digital tools: If any user/business data is collected, inadequate data protection measures or unclear consent mechanisms may create legal/compliance risks and reputational harm.

- Force majeure and external events: Unforeseen events (extreme weather, public health incidents, security incidents) may affect event delivery, travel, and timelines.

Risk mitigation (general): The Contractor shall propose practical mitigation measures in its workplan (e.g., clear approval milestones, buffer times, supplier confirmations, QA procedures, alternative options for venues/transport, phased testing for digital outputs, and documented rights management).

# SCOPE OF THE WORK

## General

### Description of the assignment

This assignment covers the provision of professional services required to support the full implementation, visibility, promotion and long-term sustainability of the Pomorie–Kırklareli Terroir & Traditions Tourism Route under the SHARE — Shared Shores & Stories: Discovering the Rich Cultural Heritage & Terroir of Pomorie–Kırklareli Tourist Area project, co-financed under the INTERREG VI-A IPA Bulgaria–Turkey Cross-Border Cooperation Programme 2021–2027.

The scope is organised into five lots, each corresponding to a distinct but complementary set of activities and outputs. Together, the lots cover the full cycle from strategic planning and brand development through to promotional production, printing, event management, digital marketing and digital tool development. The detailed specific objectives, expected outputs and technical requirements for each lot are defined in Section 4.2. of these Terms of Reference and constitute the primary reference for the performance of services.

Lot 1 — Strategy Development covers the preparation of an integrated strategic framework for the tourism route, including a SWOT analysis, stakeholder mapping and engagement, market research and a practical sustainable tourism practices guide. These outputs provide the evidence base and strategic direction needed to guide the long-term development and management of the cross-border tourism route.

Lot 2 — Creative Design and Visual Production Services covers two complementary streams. The first stream (BC 4.4) focuses on the development of a unified corporate identity and brand narrative for the tourism route, including a logo and visual identity system, brand guidelines, a corporate identity booklet and standardised design templates. The second stream (BC 4.5) covers the production of high-quality visual and promotional content, including a custom illustrated route map, promotional print materials (brochures, visitor guides, postcards), a professional photography library of at least 200 edited images covering both regions, and three thematic promotional films of approximately 60 seconds each.

Lot 3 — Printing Services covers the professional printing and delivery of the promotional materials designed under Lot 2, specifically 1,000 copies each of maps, brochures, visitor guides and postcards, to be distributed in both Kırklareli (Türkiye) and Pomorie (Bulgaria) for public use.

Lot 4 — PR, Organisation & Event Management and Travel Services covers a broad set of interconnected activities: organisation and logistics for the Partners' Meeting in Kırklareli (BC 4.1); transportation and vehicle allocation for 25 participants on the Kırklareli–Pomorie round trip (BC 4.3); professional PR management, multichannel digital marketing and promotion including press releases, editorial content, media familiarisation trips, social media management, SEO and influencer collaborations (BC 4.7); and planning and delivery of the two-day Terroir & Traditions Festival in Türkiye for approximately 50 participants (BC 4.8).

Lot 5 — Digital & Green Transformation Activities covers the design and development of a smart mobile application and complementary website for the Pomorie–Kırklareli Terroir & Traditions Tourism Route (BC 4.9), including offline functionality and an integrated sustainability tracking and reporting module enabling tourism businesses and visitors to measure, monitor and report their environmental impact along the route.

Across all lots, the Contractor(s) shall ensure timely delivery of all outputs in accordance with the agreed workplan and schedule, and shall coordinate closely with the Contracting Authority and relevant stakeholders. Throughout implementation, the Contractor(s) shall be responsible for: (i) day-to-day coordination and communication with the Contracting Authority; (ii) quality assurance of all deliverables prior to submission; (iii) full compliance with the project's communication and visibility requirements as laid down by the European Commission and the INTERREG VI-A IPA Bulgaria–Turkey Programme; (iv) provision of evidence and documentation for the acceptance and verification of outputs; and (v) submission of required reports and documentation as specified in Section 7 of these Terms of Reference.

Activities not explicitly included in the lot descriptions under Section 4.2, or not agreed in writing by the Contracting Authority, shall be considered outside the scope of this assignment.

### Geographical area to be covered

Programme Area, Kırklareli, Pomorie

### Target groups

The main target groups of the assignment are:

- Local and regional stakeholders in Türkiye (Kırklareli) and Bulgaria (Pomorie), including municipalities, tourism boards and public institutions involved in destination development and route management.

- Tourism sector actors along the route, such as accommodation providers, tour operators/guides, wineries and vineyards, restaurants, local producers, artisan workshops and event organisers.

- Civil society and local communities, including community groups and local initiatives contributing to cultural heritage and sustainable tourism.

- Visitors and potential visitors interested in nature-based and sustainable travel, including nature enthusiasts, eco-conscious travellers, adventure seekers and cultural explorers.

- Media and multipliers, including travel journalists, bloggers, influencers, editorial platforms and tourism experts who can amplify visibility and outreach.

## Specific work

This section sets out the major tasks and requirements to be fulfilled by the Contractor(s) under each lot. It is not prescriptive as to the methodology or internal organisation of the Contractor(s); tenderers are expected to prepare their own detailed Organisation and Methodology in response to the requirements set out below. Tasks are presented lot by lot, in broadly chronological order within each lot. All tasks requiring specific expertise are identified accordingly. Reference is made throughout to the reporting requirements set out in Section 7.

Across all lots and throughout the entire period of implementation, the Contractor(s) shall comply with the latest Communication and Visibility Requirements for EU-funded external actions as laid down and published by the European Commission, and with the specific visibility rules of the INTERREG VI-A IPA Bulgaria–Turkey Programme. Compliance with visibility requirements shall be treated as a standalone output of the contract, and the Contractor(s) shall report on all visibility-related actions taken in each progress and final report submitted under Section 7.

Lot 1 — Strategy Development

(BC 4.2 — Strategy Management & Integration, SWOT Analysis, Stakeholder Engagement, Market Research and Sustainable Tourism Practices Guide)

Task 1.1 — Inception and workplan (Week 1–2) Upon contract signature, the Contractor shall prepare an inception note confirming the methodology, stakeholder engagement approach, data collection plan and timeline for all deliverables under this lot. The inception note shall be submitted as part of the Inception Report required under Section 7.

Task 1.2 — Stakeholder mapping and engagement (Months 1–2 | Stakeholder Engagement Specialist) The Contractor shall identify, map and engage all relevant stakeholders in both Kırklareli and Pomorie, including local authorities, tourism boards, accommodation providers, tour operators, vineyards, local producers, artisan workshops and civil society organisations. Stakeholder consultations shall be conducted through interviews, focus groups or workshops as appropriate. Findings shall be documented in the Stakeholder Mapping and Engagement Report and shall feed directly into the strategic framework and market research tasks.

Task 1.3 — SWOT analysis (Months 1–2 | Tourism Analyst) The Contractor shall conduct a systematic SWOT analysis of the Pomorie–Kırklareli cross-border tourism area, drawing on desk research, field observations and stakeholder input gathered under Task 1.2. The analysis shall cover the competitive position of the joint destination, its tourism assets and constraints, and opportunities arising from cross-border cooperation. Findings shall be presented in the SWOT Analysis Report.

Task 1.4 — Market research (Months 2–4 | Market Researcher) The Contractor shall carry out targeted market research to identify key visitor segments, demand trends, competitor destinations and market positioning opportunities for the Pomorie–Kırklareli tourism route. Research shall draw on both primary data (visitor surveys, operator interviews) and secondary sources (programme data, national tourism statistics, comparable destination benchmarks). Findings shall be presented in the Market Research Report and shall directly inform the strategic framework.

Task 1.5 — Development of the Integrated Strategic Framework (Months 1–4 | Strategy Expert) Drawing on the outputs of Tasks 1.2–1.4, the Contractor shall develop a comprehensive Integrated Strategic Framework for the long-term development and management of the Pomorie–Kırklareli Terroir & Traditions Tourism Route. The framework shall define strategic priorities, a results chain, key actions and responsibilities, a sustainability roadmap and coordination mechanisms for cross-border route management. The document shall be produced in English and Turkish (approximately 25-30 pages each) and submitted in draft for review before finalisation.

Task 1.6 — Sustainable Tourism Practices Guide (Months 2–4 | Sustainability Consultant) The Contractor shall develop a practical Sustainable Tourism Practices Guide for use by tourism businesses, local authorities and other route stakeholders. The guide shall provide actionable guidance on environmentally responsible operations, green transition measures and sustainability standards applicable to the Pomorie–Kırklareli tourism context. It shall be produced in English and Turkish (approximately 5 pages each).

Task 1.7 — Reporting (see Section 7) The Contractor shall submit an Inception Report within the deadline specified in Section 7, a draft final report no later than one month before the end of the implementation period, and a final report incorporating comments received. All reports shall document progress against the indicators defined in Section 8.1 and shall include a dedicated section on compliance with EU and programme visibility requirements.

Duration: The duration of the assignment is foreseen to be a total of approximately four (4) months from the date of signature of the contract. The deliverables are expected to be submitted progressively between April 2026 and 01/08/2026.

Lot 2 — Creative Design and Visual Production Services

(BC 4.4 — Corporate Identity; BC 4.5 — Mapping, Promotional Materials, Photography & Films)

Task 2.1 — Inception and brand brief alignment (Week 1–2) The Contractor shall hold a kick-off meeting with the Contracting Authority to confirm the brand direction, visual preferences, content priorities, target audiences and approval process. An inception note shall be submitted as part of the Inception Report under Section 7.

Task 2.2 — Common brand story and messaging framework (Months 1–2 | Narrative Creation Expert, Content Researcher) The Contractor shall develop a compelling Common Brand Story and Messaging Framework for the tourism route, covering brand essence, values, positioning, target audiences, tone of voice, key message pillars and tagline options. The narrative shall draw on the cultural, gastronomic and eco-tourism assets of both Kırklareli and Pomorie and shall be submitted in draft for approval before finalisation.

Task 2.3 — Logo and visual identity development (Months 1–3 | Graphic Designer, Visual Identity Specialist) The Contractor shall design a primary logo and core visual identity set for the tourism route, including colour palette, typography system and logo variations. All elements shall be delivered with full technical specifications (CMYK, RGB, HEX values) and usage rules. The Visual Identity Guidelines / Corporate Identity Booklet shall consolidate all brand rules into a single coherent booklet delivered in print-ready and screen-optimised versions.

Task 2.4 — Standardised design templates (Months 1-3 | Graphic Designer) The Contractor shall produce a minimum set of editable standardised templates, including a presentation template (PPTX), an A4 flyer template, a tri-fold brochure template and a roll-up/poster template, all aligned with the approved visual identity. Templates shall be delivered in editable source formats with PDF exports.

Task 2.5 — Asset mapping and content collection (Months 1–3 | Tourism Researcher, Field Photographer/Drone Operator) The Contractor shall carry out a comprehensive mapping of eco-tourism and cultural assets in both Kırklareli and Pomorie, including eco-tourism resorts, vineyards, glamping sites, natural parks, tourism centres and historical sites. Mapped assets shall be compiled into a structured Asset Mapping and Content Pack with standardised fields (name, category, description, location, thematic tag) for direct use in subsequent design tasks.

Task 2.6 — Custom illustrated tourism route map (Months 3–4 | Illustrator/Graphic Designer) Using the asset mapping output, the Contractor shall design a Custom Illustrated Tourism Route Map showing key points of interest, thematic routes, cross-border links and a bilingual-ready layout. The map shall be delivered in editable source files, print-ready CMYK PDF, digital RGB PDF and web image exports.

Task 2.7 — Design of promotional print materials (Months 5–8 | Graphic Designer) The Contractor shall design a coherent set of promotional print materials, including at minimum one brochure, one visitor guide and one postcard set, fully aligned with the approved visual identity. All items shall be delivered in editable source files, print-ready PDFs and digital PDFs. Designs shall be submitted for written approval by the Contracting Authority before being released for printing under Lot 3.

Task 2.8 — Professional photography and drone shooting (Months 2–8 | Field Photographer/Drone Operator) The Contractor shall carry out professional photography and drone shooting sessions in both Kırklareli and Pomorie, delivering a minimum of 200 professionally edited photographs covering all defined asset categories. The photographs shall be taken across different seasons and during relevant events/activities along the tourism route, in order to reflect year-round attractiveness and authentic visitor experiences. The Contractor shall propose an indicative shooting plan (locations, seasons and event opportunities) for the Contracting Authority’s approval. Images shall be delivered in high-resolution and web-optimised versions, with a structured folder library, consistent file naming and a metadata/caption list.

Task 2.9 — Production of thematic promotional films (Months 2–8 | Videographer/Director, Video Editor) The Contractor shall produce three thematic promotional films of approximately 60 seconds each, reflecting the route pillars (eco-tourism, cultural heritage, gastronomy or other approved themes). Films shall be delivered in Full HD (minimum 1920×1080) MP4 format, with one master version and one web/social-optimised version per film. All music and sound elements shall have cleared usage rights.

Task 2.10 — Reporting (see Section 7) The Contractor shall submit an Inception Report, a draft final report and a final report in accordance with the requirements of Section 7, including documentation of compliance with EU and programme visibility requirements across all deliverables.

Duration: The duration of the assignment is foreseen to be a total of approximately seven (7) months from the date of signature of the contract. The deliverables are expected to be submitted progressively between April 2026 and 01/11/2026.

Lot 3 — Printing Services

(BC 4.6 — Common Route Creation Activities in Türkiye — Printing of Promotional Materials)

Task 3.1 — Pre-press verification and proofing (Month 1 after artwork receipt) Upon receipt of final artwork files from the Contracting Authority, the Contractor shall verify all files for print readiness (bleed, trim marks, colour profile, resolution) and prepare digital proofs for each item. Where requested, one physical proof per item shall also be provided. Mass printing shall only commence following written approval by the Contracting Authority.

Task 3.2 — Printing of promotional materials The Contractor shall print the following quantities to professional quality standards:

| Item | Quantity |
| --- | --- |
| Maps | 1,000 copies |
| Brochures | 1,000 copies |
| Visitor Guides | 1,000 copies |
| Postcards | 1,000 copies |

All items shall be printed using professional offset or high-quality digital printing, consistent in colour and layout across the full quantity, and free from production defects. Paper and finishing specifications shall comply with the following minimum standards:

- Maps: Durable paper suitable for handling and folding (135–170 gsm), with clean trimming and folding as applicable.

- Brochures: Coated paper (115–135 gsm for cover and inner pages), folded/stapled or perfect-bound as required by the layout.

- Visitor guides: Higher-durability finish (cover 200–250 gsm; inner 135–150 gsm), binding as required by the layout.

- Postcards: Rigid cardstock (200–250 gsm), matte or gloss finish as per artwork, with clean edges.

Task 3.3 — Quality inspection and delivery Prior to dispatch, the Contractor shall carry out a quality acceptance inspection and document results against a checklist. Printed materials shall be delivered to Kırklareli (Türkiye) in protective packaging, with signed delivery notes.

Task 3.4 — Reporting (see Section 7) The Contractor shall submit a final report confirming delivery quantities, quality compliance and any deviations from specifications, together with signed delivery notes and photographic documentation, in accordance with Section 7.

Duration: The duration of the assignment is foreseen to be a total of approximately eight (8) months from the date of signature of the contract. The deliverables are expected to be submitted progressively between April 2026 and 01/12/2026.

Lot 4 — PR, Organisation & Event Management and Travel Services

(BC 4.1 — Partners' Meeting; BC 4.3 — Travel; BC 4.7 — PR & Digital Marketing; BC 4.8 — Festival)

Task 4.1 — Inception and coordination plan (Week 1–2) The Contractor shall prepare an inception note confirming the coordination approach, priority activities, communication channels, approval steps and implementation timetable for all budget components under this lot. The inception note shall be submitted as part of the Inception Report under Section 7.

Task 4.2 — Organisation of the Partners' Meeting in Kırklareli (Months 1–2  ) The Contractor shall organise and deliver the Partners' Meeting in Kırklareli, including preparation and printing of meeting documents (agenda, progress report, timeline, task allocation chart), provision of a professional translator for the full duration of the meeting, and organisation of one coffee break with light refreshments. All meeting materials shall be delivered to the venue before the meeting. The Contractor shall liaise with the Contracting Authority to confirm the date, duration, participant number and any special requirements.

Task 4.3 — Travel and vehicle allocation (Months 4-5 | Travel/Transport Coordinator) The Contractor shall organise transport services for 25 participants on the Kırklareli–Pomorie–Kırklareli route (total 280 km) and allocate one appropriate vehicle to the Trakya Development Agency for three consecutive days, including a qualified licensed driver and all operational costs (fuel, tolls, parking). The Contractor shall coordinate with the Contracting Authority to confirm departure and return times, pick-up and drop-off points and any intermediate stops.

Task 4.4 — PR management and multichannel promotion (Months 1-15 | PR Specialist, Social Media Manager, Content Creator, SEO Specialist, Digital Marketer, Travel Writer, Influencer Manager) The Contractor shall develop and implement a PR & Multichannel Promotion Plan covering key messages, target audiences, communication channels and an implementation timetable. Under the plan, the Contractor shall:

- Prepare and disseminate press releases to a targeted media list, with distribution reporting;

- Produce editorial content for travel magazines and newspapers, including drafts for approval and final versions;

- Organise and coordinate media familiarisation trips for selected journalists, bloggers and influencers, including planning, logistics and on-site support;

- Implement influencer and expert collaborations, including coordination, content guidance, publication scheduling and performance reporting;

- Manage social media channels through content planning, posting, community management and performance tracking;

- Implement SEO-oriented digital marketing activities to improve the discoverability of route content across agreed platforms and channels.

All draft content shall be submitted for approval by the Contracting Authority before publication or dissemination. The Contractor shall provide brief activity reports covering delivered outputs, links/clippings and basic performance metrics (reach, engagement, coverage).

Task 4.5 — Two-day Terroir & Traditions Festival in Türkiye (Months 12-15 | Event Coordinator, Technical Crew, Hospitality Manager, Transport Coordinator) The Contractor shall plan, organise and manage a two-day Terroir & Traditions Festival in Türkiye for approximately 50 participants from Bulgaria and Türkiye. Tasks shall include: detailed event planning and agenda preparation; on-site management throughout both days; venue set-up, decoration and provision of technical equipment (stage, sound, lighting); accommodation for approximately 50 participants for two nights in a minimum 3-star hotel; catering providing three meals per day per participant; and provision of buses/vans for participant transport related to the festival programme. The Contractor shall submit a completion report including the final agenda, attendance sheet, photographic documentation and confirmation of services delivered, in accordance with Section 7.

Task 4.6 — Reporting (see Section 7) The Contractor shall submit an Inception Report, progress report(s) as required, a draft final report and a final report in accordance with Section 7, documenting delivery of all outputs and compliance with EU and programme visibility requirements.

Duration: The duration of the assignment is foreseen to be a total of  approximately fifteen (15) months from the date of signature of the contract. The deliverables are expected to be submitted progressively between April 2026 and 01/07/2027.

Lot 5 — Digital & Green Transformation Activities

(BC 4.9 — Development of Smart Mobile App & Website for the Sustainable Tourism Route)

Task 5.1 — Inception, requirements definition and workplan (Week 1–2 | Project Manager) The Contractor shall hold a kick-off meeting with the Contracting Authority to confirm the functional requirements, content scope, branding/visibility rules, platform targets, hosting arrangements and acceptance criteria for the mobile application and website. An inception note shall be submitted as part of the Inception Report under Section 7.

Task 5.2 — UI/UX design and information architecture (Months 1–3 | UI/UX Designer) The Contractor shall develop the information architecture, user flows and UI/UX design for both the mobile application and the website. Design shall be user-centred, intuitive and suitable for tourist audiences, with consistent branding aligned to the visual identity developed under Lot 2. Design prototypes shall be submitted for review and approval by the Contracting Authority before development commences.

Task 5.3 — Mobile application development (Months 2–5 | App Developer) The Contractor shall design and develop a smartphone mobile application showcasing eco-friendly tourism experiences, cultural activities and local attractions along the Pomorie–Kırklareli route. The application shall include structured content by category (vineyards, nature routes, cultural events, artisan workshops), an interactive map, itinerary functionality and a content management mechanism allowing the Contracting Authority to update information after deployment.

Task 5.4 — Sustainability tracking and reporting module (Months 3–6 | App Developer, Sustainability Consultant) The Contractor shall develop an integrated sustainability tracking and reporting module enabling tourism businesses and visitors to input sustainability-related data (transport mode, activity type, basic consumption proxies), view simple progress indicators and generate a basic report or export. The module shall include explanatory guidance on eco-friendly practices and shall be understandable to non-expert users. Methodological definitions and reporting format shall be agreed with the Contracting Authority during implementation.

Task 5.5 — Website development (Months 2–5 | Web Developer) The Contractor shall develop a complementary website aligned with the mobile application in design, branding and content, ensuring a consistent user experience across platforms. The website shall be optimised for usability, accessibility and performance, and shall include a practical content management system or equivalent mechanism for post-deployment updates by the Contracting Authority.

Task 5.6 — Content creation and structuring (Months 2–6 | Content Writer) The Contractor shall provide and structure content for both the mobile application and website, covering eco-tourism activities, vineyard experiences, nature routes, cultural events and artisan workshops in both Kırklareli and Pomorie. Content shall be presented in a consistent template format, audience-appropriate and aligned with the route's sustainability values and EU visibility requirements.

Task 5.7 — Testing, quality assurance and finalisation (Month 6-10 | QA Tester) The Contractor shall carry out functional, usability and basic compatibility testing across target devices and platforms, and shall resolve all identified defects prior to final delivery. Acceptance shall be based on: (i) delivery of all modules (application, website, sustainability tracking); (ii) usability and stability; (iii) provision of basic user guidance and technical documentation; and (iv) compliance with agreed branding and visibility requirements.

Task 5.8 — Final delivery and documentation (Month 10-15 | Project Manager) The Contractor shall deliver the fully functional mobile application and website, ready for deployment on relevant platforms, together with basic user guidance (admin/content update instructions) and technical handover documentation. Source files, credentials and all project assets shall be handed over to the Contracting Authority.

Task 5.9 — Reporting (see Section 7) The Contractor shall submit an Inception Report, a draft final report and a final report in accordance with Section 7, documenting the delivery of all modules and outputs, test results, any deviations from the agreed specifications and compliance with EU and programme visibility requirements.

Duration: The duration of the assignment is foreseen to be a total of approximately fifteen (15) months from the date of signature of the contract. The deliverables are expected to be submitted progressively between April 2026 and 01/07/2027.

## Project management

### Responsible body

Trakya Development Agency will be responsible for managing the contract

### Management structure

The Contracting Authority (Trakya Development Agency) will manage the contract through its Project Management Unit, acting as the Project Coordinator for the purposes of the General Conditions.

Project Management Unit (PMU): The Project Coordinator and the Contracting Authority’s project team are responsible for day-to-day contract management, including coordination with the contractor(s), planning, monitoring of progress, review of deliverables and organisation of approvals/acceptance.

Implementation will be planned through an agreed workplan and timetable (submitted by the contractor(s) and validated by the Contracting Authority). Progress will be monitored through regular coordination (meetings/calls/emails as needed) and reporting as defined in Section 7 (Reports) and Section 8 (Monitoring and Evaluation). Deliverables will follow a draft–review–final cycle, with consolidated feedback provided by the Contracting Authority (and partner inputs where relevant).

In accordance with Article 20 of the General Conditions, the Project Coordinator may take day-to-day operational decisions necessary for the implementation of the contract, including for example:

- approval of routine coordination arrangements and operational planning (meeting agendas, schedules, logistics details);

- validation of non-substantial adjustments that do not affect the scope, budget, key deliverables or contractual deadlines (e.g. minor timetable refinements, minor editorial changes);

- acceptance or request for revision of deliverables in line with the Terms of Reference and agreed quality standards;

- confirmation of routine communications and instructions to the contractor(s) required for contract implementation.

Decisions that imply a substantial change (including any change affecting the scope of services, key outputs, budget, contract duration/implementation period, or other contractual conditions) shall require prior authorisation by the Contracting Authority in accordance with its internal procedures and, where applicable, consultation with the project steering/coordination mechanism and/or the Partner administration. Any such changes shall be formalised in writing in line with the applicable contractual provisions.

### Facilities to be provided by the contracting authority and/or other parties

N/A

# LOGISTICS AND TIMING

## Location

The place of performance under this contract includes home-based/remote work and on-site missions as required to deliver the expected outputs.

- (a) Home-based / remote

The following activities may be carried out primarily on a home-based/remote basis, with regular coordination with the Contracting Authority:

- strategy development and drafting of documents (Lot 1 / BC 4.2);

- branding, design, layout and preparation of print-ready and digital files (Lot 2 / BC 4.4–BC 4.5);

- preparation of PR materials, editorial content, social media planning, SEO-oriented content and reporting (Lot 4 / BC 4.7);

- development and testing of the mobile application and website, including offline functionality and sustainability tracking/reporting features (Lot 5 / BC 4.9).

- (b) Mission / on-site locations (minimum requirements)

On-site presence and/or service delivery is required for the following components:

- Türkiye (Kırklareli): Partners’ Meeting implementation support (Lot 4 / BC 4.1); Two-day Festival delivery (Lot 4 / BC 4.8); any on-site coordination as required.

- Bulgaria (Pomorie): On-site coordination as required for cross-border activities and partner engagement; and any other outputs requiring presence in Pomorie.

- Cross-border travel route: Transport services between Kırklareli and Pomorie as specified (Lot 4 / BC 4.3).

- (c) Delivery locations for physical outputs

Printed materials under Lot 3 (BC 4.6) shall be delivered to designated addresses in Türkiye (Kırklareli), as confirmed by the Contracting Authority during implementation.

- (d) Minimum delivery mode

The Contractor shall ensure the capacity to:

- attend and support on-site activities in Kırklareli and, where required, in Pomorie;

- deliver physical outputs to Kırklareli; and

- provide remote coordination, draft submissions and digital deliveries through electronic means (email/shared links/platforms) as agreed with the Contracting Authority.

Exact addresses, venues and dates for missions/on-site activities shall be confirmed by the Contracting Authority during implementation.

## Start date & period of implementation of tasks

The intended start date is April 2026 and the maximum period of implementation of the contract will be 15 months from this date. The duration of the assignment is foreseen to be a total of approximately fifteen (15) months from the date of signature of the contract. The deliverables are expected to be submitted progressively between April 2026 and 01/07/2027. For lot-specific implementation periods, please refer to Section 2.2 and point 3 of the main conditions, which prevail.

# REQUIREMENTS

## Personnel

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be able to provide input as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well on any potential interference or conflict of interest of the proposed expert in his/her function as expert and his/her present or previous functions working as civil servant. Moreover proof should be submitted that the expert is seconded or on personal leave.

The selection procedures used by the contractor to select the experts who provide input to the contract must be transparent, must guarantee the absence of professional conflicting interests and the absence of any discrimination based on former or current nationality, gender, place of residence, or any other ground. The findings of the selection panel must be recorded.

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

### Experts

Note on contract type: This is a global price contract. The Contracting Authority does not request individual expert profiles (CVs), statements of exclusivity or statements of availability as part of the tender. It is the contractor's responsibility to assign the appropriate personnel to deliver the required outputs. The team composition described in the Organisation and Methodology is indicative and for assessment purposes only; it does not constitute a contractual commitment regarding specific named individuals.

Since this assignment is organised in lots, minimum requirements are defined separately for each lot. Tenderers shall submit an offer for one or more lots and shall demonstrate that their proposed team, taken as a whole, meets the minimum requirements applicable to each lot for which an offer is submitted. Compliance will be verified on a yes/no basis; no marks will be awarded for the composition or qualifications of the team of experts.

The Organisation and Methodology shall demonstrate how the proposed team as a whole meets the requirements below and how the relevant expertise will be deployed to deliver the expected outputs of the relevant lot(s).

Where an individual expert covers more than one area of expertise, this shall be clearly demonstrated in the Organisation and Methodology.

Lot 1 — Strategy Development

- Experience in tourism planning, destination management or regional development strategy, preferably in a cross-border or international cooperation context.

- Experience in conducting stakeholder consultations, participatory research or engagement processes in the tourism, regional development or public policy sector.

- Familiarity with sustainable tourism principles, green transition frameworks or relevant EU sustainability guidelines.

Lot 2 — Creative Design and Visual Production Services

- Proven experience in brand identity development and visual communication design for tourism, cultural heritage or destination promotion purposes, evidenced by a portfolio of comparable completed assignments.

- Professional experience in photography and videography for promotional purposes, including experience with drone operations where applicable.

- Experience in designing multilingual promotional materials (brochures, maps, guides or equivalent) intended for public distribution.

Lot 3 — Printing Services

- Proven capacity to produce professional offset or high-quality digital printing of promotional materials (maps, brochures, visitor guides, postcards or equivalent) in quantities comparable to those required under this lot.

Lot 4 — PR, Organisation & Event Management and Travel Services

- Proven experience in public relations and/or multichannel digital marketing, including social media management, press relations and influencer or editorial outreach, preferably in the tourism or cultural sector.

- Experience in organising and managing public events or festivals involving participants from more than one country.

- Familiarity with EU-funded project communication and visibility requirements, or equivalent public sector communication standards.

Lot 5 — Digital & Green Transformation Activities

- Proven experience in the design and development of mobile applications and/or websites for tourism, cultural heritage, environmental or comparable public-facing purposes, evidenced by at least one comparable completed project.

### Support facilities & backstopping

The costs for support facilities, including backstopping, are included in the tenderer's financial offer.

## Office accommodation

Office accommodation shall be provided by the Contractor. Meeting/training/event venues (where applicable) will be provided/confirmed by the Contracting Authority as part of the activity arrangements.

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

The Contractor shall provide, at its own cost, all equipment, tools and services required for successful delivery of the outputs, including, as applicable: computers and peripherals, software licences/subscriptions, communication costs, project management tools, design/production tools, testing devices/environments for digital outputs, and any other resources required to deliver the services in accordance with these Terms of Reference. The Contractor shall also ensure timely internal financial arrangements to support implementation and shall ensure that its personnel are paid regularly and in a timely manner.

The Contracting Authority and, where relevant, the Partner shall provide timely access to necessary inputs and documentation required for implementation (e.g. existing project materials, route content inputs, contact points, branding/visibility guidance, approvals and confirmations). Where on-site events/meetings are part of the scope, the Contracting Authority/Partner shall confirm key operational parameters (dates, locations, estimated participants) and facilitate access to relevant stakeholders, while the Contractor remains responsible for delivering the services included in the lot(s) awarded.

As this is a global price contract, no reimbursable or incidental expenditure shall be payable unless explicitly provided for in the contract. Tenderers must therefore ensure that their financial offer covers all costs necessary to deliver the outputs.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English in one original and 1 electronically (PDF, and where relevant editable formats)  copies:

Inception Report of maximum 12 pages to be produced after one week from the start of implementation. In the report the contractor shall describe e.g. initial findings, progress in collecting data, any difficulties encountered or expected in addition to the work programme and staff travel. The contractor should proceed with his/her work unless the contracting authority sends comments on the inception report.

"Given that this contract is organised in lots with varying implementation periods, one (1) Interim Progress Report shall be submitted by the Contractor at the midpoint of each lot's implementation period, as follows:

- Lot 1 (4 months): end of Month 2

- Lot 2 (7 months): end of Month 4

- Lot 3 (8 months): end of Month 4

- Lot 4 (15 months): end of Month 8

- Lot 5 (15 months): end of Month 8

The Interim Progress Report shall be of maximum 3 pages per lot (or consolidated) and shall include:

- Summary of outputs delivered and activities completed during the reporting period, with reference to the workplan milestones

- Status of outputs in progress, including any deviations from the agreed schedule and corrective actions taken or planned

- Updated risk register with any new risks identified and mitigation measures applied

- Financial summary of expenditure incurred during the reporting period (where applicable under the contract)

- Documentation of visibility and communication actions carried out, including samples or links where available

- Any issues requiring a decision or guidance from the Contracting Authority

Interim payments may be authorised on the basis of approval of the Interim Progress Report, demonstrating that specific objectives and intermediate outputs have been reached, in accordance with Article 29 of the General Conditions.

Draft final report of maximum 10 pages (main text, excluding annexes).  This report shall be submitted no later than one month before the end of the period of implementation of tasks. The Draft Final Report shall include:

- A comprehensive description of all outputs delivered under the contract, with reference to the expected outputs defined in Section 2 and the indicators defined in Section 8.1

- Assessment of the extent to which the specific objectives (outcomes) and overall objective have been achieved or are on track

- Lessons learned and recommendations for the sustainability and further development of the Pomorie–Kırklareli Terroir & Traditions Tourism Route after the end of the contract

- Full documentation of visibility and communication compliance throughout the implementation period

- All supporting annexes, including approved deliverables, delivery notes, attendance sheets, media clippings, analytics extracts, signed documents and photographic documentation as relevant per lot.

Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 15 days after receipt of comments on the draft final report. The report shall contain a sufficiently detailed description of the different options to support an informed decision on the approval and acceptance of the delivered outputs across all lots, and the prioritisation of follow-up actions to ensure sustainability, effective dissemination and long-term use of the project results. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the project manager/coordinator identified in the contract. The project manager is responsible for approving the reports.

Reports shall be submitted electronically to the Project Manager / Coordinator identified in the contract. The Project Manager is responsible for coordinating the review process and approving the reports.

As a standard practice, the Partner administration (Municipality of Pomorie) shall be involved in the review of reports and deliverables, in particular for activities and outputs implemented in Bulgaria and/or jointly with the Partner. The Project Manager / Coordinator shall consolidate comments received from the Partner and the Contracting Authority and transmit consolidated feedback to the Contractor.

Unless otherwise agreed, the Partner shall provide its comments within 10 calendar days from receipt of the report/deliverable for review. In the absence of comments from the Partner within this deadline, the report/deliverable shall be deemed to be approved by the Partner for the purposes of the review process. Final approval remains with the Project Manager / Coordinator.

# MONITORING AND EVALUATION

## Definition of indicators

The Contractor shall monitor progress and report on the achievement of the expected results using practical and verifiable indicators. Indicators will be applied per lot and will focus on: (i) timely delivery and approval of outputs, and (ii) basic reach/uptake where relevant. Evidence supporting each indicator (verification sources) shall be provided together with the reports defined in Section 7 (e.g. approved deliverables, links, screenshots, test/QA reports, attendance lists, delivery notes, photo documentation, media clippings and analytics extracts).

Minimum indicators per lot (to be reported):

- Lot 1 (Strategy – BC 4.2): All strategic documents and the Sustainable Tourism Practices Guide delivered and approved; stakeholder engagement evidence provided.

- Lot 2 (Creative – BC 4.4–4.5): Brand/visual identity package and creative assets (design files, photo/video outputs) delivered and approved; technical compliance confirmed.

- Lot 3 (Printing – BC 4.6): Required quantities printed and delivered to Kırklareli and Pomorie; print quality and acceptance confirmed.

- Lot 4 (PR/Events/Travel – BC 4.1/4.3/4.7/4.8): Meeting, travel service and festival delivered as planned; PR outputs implemented (plan, press releases, content, fam trip(s), influencer collaborations); basic visibility evidence and performance summary provided.

- Lot 5 (Digital – BC 4.9): Mobile app and website delivered ready for deployment; offline functionality and sustainability tracking/reporting implemented; testing/acceptance evidence and documentation delivered.

Where applicable, the Contractor shall also provide a short summary of visibility and dissemination actions and results (media/social/digital analytics) as part of the reporting.

## Special requirements

N/A

* * *